## Service Over Under
Service Over/Under
Seattle Area From Period: 10/5/2014 To 11/8/2014 | [5 empty] | Call Type: GENERATED MC
Contract | Location | Type | Service Call | Call Status | Call Cmpl Date | Technician | Tech Team | Appt Date | Actual Hours | Est Task Hours | Hours Variance
10400 | WEST SEATTLE DENTAL CLINIC | S | 140808-0032 | CLOSED | 10/08/14 | INGLEK | HVAC SEATTLE | 10/08/14 | 1.5
[6 empty] | 140808-0032 Total |  |  | 1.5 | 1.53 | -0.03
|  | S | 140808-1579 | CLOSED | 10/08/14 | INGLEK | HVAC SEATTLE | 10/08/14 | 3
[6 empty] | 140808-1579 Total |  |  | 3 | 2.99 | 0.01
11334 | 83 KING BUILDING | S | 140808-0810 | CLOSED | 10/16/14 | JACKSONK | HVAC SEATTLE | 10/16/14 | 3.6
[6 empty] | 140808-0810 Total |  |  | 3.6 | 3.6 | 0
|  | S | 140808-0953 | CLOSED | 10/21/14 | OLSONB | HVAC SEATTLE | 10/21/14 | 8
[6 empty] | 140808-0953 Total |  |  | 8 | 6.49 | 1.51
|  | S | 140808-1259 | CLOSED | 10/24/14 | HODGINSJ | Seattle Area | 10/24/14 | 6
[6 empty] | BATEE | Seattle Area | 10/20/14 | 8
[6 empty] | BATEE | Seattle Area | 10/21/14 | 11
[6 empty] | BATEE | Seattle Area | 10/24/14 | 8
[6 empty] | HODGINSJ | Seattle Area | 10/24/14 | 8
[6 empty] | HODGINSJ | Seattle Area | 10/24/14 | 8
[6 empty] | OLSONB | Seattle Area | 10/22/14 | 1
[6 empty] | BATEE | Seattle Area | 10/23/14 | 8
[6 empty] | HODGINSJ | Seattle Area | 10/24/14 | 8
[6 empty] | BATEE | Seattle Area | 10/24/14 | 8
[6 empty] | HODGINSJ | Seattle Area | 10/24/14 | 8
[6 empty] | 140808-1259 Total |  |  | 82 | 115.39 | -33.39
11334CNT | 83 KING BUILDING | S | 140808-1477 | CLOSED | 10/21/14 | ZELLERT | HVAC SEATTLE | 10/21/14 | 3.75
[6 empty] | 140808-1477 Total |  |  | 3.75 | 3.75 | 0
11376 | DSHS | S | 140411-0297 | CLOSED | 10/10/14 | REGHETAO | HVAC SEATTLE | 10/10/14 | 1.25
[6 empty] | 140411-0297 Total |  |  | 1.25 | 1 | 0.25
|  | S | 140613-0300 | CLOSED | 10/10/14 | REGHETAO | HVAC SEATTLE | 10/10/14 | 1
[6 empty] | 140613-0300 Total |  |  | 1 | 1 | 0
11753 | LIGHTHOUSE FOR THE BLIND | C | 140808-0284 | CLOSED | 10/13/14 | INGLEK | HVAC SEATTLE | 10/09/14 | 0.75
[6 empty] | INGLEK | HVAC SEATTLE | 10/10/14 | 2.5
[6 empty] | INGLEK | HVAC SEATTLE | 10/13/14 | 6
[6 empty] | 140808-0284 Total |  |  | 9.25 | 9.1 | 0.15
|  | C | 140808-0459 | CLOSED | 10/10/14 | WILDERG | HVAC SEATTLE | 10/10/14 | 7.5
[6 empty] | WILDERG | HVAC SEATTLE | 10/10/14 | 0.5
[6 empty] | 140808-0459 Total |  |  | 8 | 8.97 | -0.97
12929 | HERITAGE HOUSE | S | 140707-1006 | CLOSED | 10/24/14 | LEEM | HVAC SEATTLE | 10/24/14 | 1.75
[6 empty] | 140707-1006 Total |  |  | 1.75 | 1.75 | 0
13438 | GALLAND SENECA BLDG | S | 140808-1351 | CLOSED | 10/09/14 | BLACKK | HVAC SEATTLE | 10/06/14 | 4.5
[6 empty] | BLACKK | HVAC SEATTLE | 10/09/14 | 3.5
[6 empty] | 140808-1351 Total |  |  | 8 | 8.5 | -0.5
13458 | TSUE CHONG COMPANY | S | 140808-0161 | CLOSED | 10/17/14 | NAVOSA | HVAC SEATTLE | 10/17/14 | 5.5
[6 empty] | 140808-0161 Total |  |  | 5.5 | 5.53 | -0.03
13482 | PORT OF SEATTLE PIER 69 | C | 140707-0788 | CLOSED | 10/10/14 | COMMERCIAC | Subcontract | 10/10/14 | 0
[6 empty] | 140707-0788 Total |  |  | 0 | 0.01 | -0.01
|  | C | 140808-0845 | CLOSED | 10/10/14 | KRUEGERJ | HVAC SEATTLE | 10/09/14 | 8
[6 empty] | KRUEGERJ | HVAC SEATTLE | 10/10/14 | 6
[6 empty] | 140808-0845 Total |  |  | 14 | 14 | 0
14069 | CASCADE DESIGN | S | 140808-0015 | CLOSED | 10/13/14 | INGLEK | HVAC SEATTLE | 10/06/14 | 6.75
[6 empty] | DIXONM | HVAC SEATTLE | 10/13/14 | 4.5
[6 empty] | INGLEK | HVAC SEATTLE | 10/07/14 | 3.75
[6 empty] | 140808-0015 Total |  |  | 15 | 10.45 | 4.55
14174 | LAKE UNION BUILDING | C | 140808-1478 | CLOSED | 10/23/14 | LEEM | HVAC SEATTLE | 10/08/14 | 1
[6 empty] | LEEM | HVAC SEATTLE | 10/09/14 | 8
[6 empty] | LEEM | HVAC SEATTLE | 10/22/14 | 2.5
[6 empty] | LEEM | HVAC SEATTLE | 10/23/14 | 2.5
[6 empty] | 140808-1478 Total |  |  | 14 | 19 | -5
14333 | BAILEY BOUSHAY HOUSE | S | 140707-0503 | CLOSED | 10/24/14 | RUFFNERK | HVAC SEATTLE | 10/06/14 | 8
[6 empty] | RUFFNERK | HVAC SEATTLE | 10/24/14 | 4
[6 empty] | 140707-0503 Total |  |  | 12 | 12.25 | -0.25
14619 | 1201 WESTERN BLDG | S | 140808-0738 | CLOSED | 10/13/14 | CHEMAQUA | Subcontract | 10/13/14 | 0.45
[6 empty] | 140808-0738 Total |  |  | 0.45 | 0.45 | 0
|  | S | 140808-0771 | CLOSED | 10/14/14 | BATEE | HVAC SEATTLE | 10/06/14 | 8
[6 empty] | HODGINSJ | HVAC SEATTLE | 10/08/14 | 8
[6 empty] | REGHETAO | HVAC SEATTLE | 10/06/14 | 4
[6 empty] | BATEE | HVAC SEATTLE | 10/07/14 | 3
[6 empty] | HODGINSJ | HVAC SEATTLE | 10/08/14 | 4
[6 empty] | BATEE | HVAC SEATTLE | 10/10/14 | 8
[6 empty] | HODGINSJ | HVAC SEATTLE | 10/13/14 | 8
[6 empty] | HODGINSJ | HVAC SEATTLE | 10/13/14 | 8
[6 empty] | HODGINSJ | HVAC SEATTLE | 10/13/14 | 8
[6 empty] | REGHETAO | HVAC SEATTLE | 10/09/14 | 8.25
[6 empty] | HODGINSJ | HVAC SEATTLE | 10/17/14 | 9
[6 empty] | BATEE | HVAC SEATTLE | 10/14/14 | 8
[6 empty] | ZELLERT | HVAC SEATTLE | 10/13/14 | 4
[6 empty] | BATEE | HVAC SEATTLE | 10/14/14 | 2
[6 empty] | 140808-0771 Total |  |  | 90.25 | 114.5 | -24.25
|  | S | 140808-0776 | CLOSED | 10/13/14 | ZELLERT | HVAC SEATTLE | 10/10/14 | 10
[6 empty] | ZELLERT | HVAC SEATTLE | 10/13/14 | 2
[6 empty] | 140808-0776 Total |  |  | 12 | 11.25 | 0.75
14671 | LASHER HOLZAPFEL SPERRY | S | 140808-0429 | CLOSED | 10/21/14 | LEEM | HVAC SEATTLE | 10/21/14 | 1.5
[6 empty] | 140808-0429 Total |  |  | 1.5 | 1.25 | 0.25
14843 | PORT OF SEATTLE PIER 66 | C | 140707-0556 | CLOSED | 10/10/14 | COMMERCIAC | Subcontract | 10/10/14 | 0
[6 empty] | 140707-0556 Total |  |  | 0 | 0.01 | -0.01
14890 | HOTEL VINTAGE SEATTLE | C | 140707-0326 | CLOSED | 10/10/14 | COMMERCIAC | Subcontract | 10/10/14 | 0
[6 empty] | 140707-0326 Total |  |  | 0 | 0.45 | -0.45
|  | C | 140808-0453 | CLOSED | 10/22/14 | SCHRAMML | CHR SEATTLE | 10/22/14 | 3
[6 empty] | 140808-0453 Total |  |  | 3 | 2.75 | 0.25
15215 | HOTEL MONACO | C | 140808-0647 | CLOSED | 10/22/14 | SCHRAMML | CHR SEATTLE | 10/22/14 | 2
[6 empty] | 140808-0647 Total |  |  | 2 | 1.5 | 0.5
15287 | SWEDISH PHYSICIANS LLC | B | 140707-0639 | CLOSED | 10/10/14 | COMMERCIAC | Subcontract | 10/10/14 | 0
[6 empty] | 140707-0639 Total |  |  | 0 | 0.01 | -0.01
15321 | ANTIOCH UNIVERSITY | C | 140707-0898 | CLOSED | 10/08/14 | LARIVIERES | HVAC SEATTLE | 10/08/14 | 1.25
[6 empty] | 140707-0898 Total |  |  | 1.25 | 1.25 | 0
15429 | US BANK #8327 RAINIER TOWER | S | 140808-0978 | CLOSED | 10/22/14 | LEEM | HVAC SEATTLE | 10/22/14 | 4
[6 empty] | 140808-0978 Total |  |  | 4 | 4 | 0
15561 | APPLIED INDUSTRIAL TECH | A | 140808-0454 | CLOSED | 10/22/14 | WHITEA | HVAC SEATTLE | 10/22/14 | 3.75
[6 empty] | 140808-0454 Total |  |  | 3.75 | 3.75 | 0
15671 | 1910 FAIRVIEW BUILDING | S | 140808-0641 | CLOSED | 10/10/14 | NAVOSA | HVAC SEATTLE | 10/03/14 | 6
[6 empty] | NAVOSA | HVAC SEATTLE | 10/06/14 | 2
[6 empty] | NAVOSA | HVAC SEATTLE | 10/08/14 | 2
[6 empty] | NAVOSA | HVAC SEATTLE | 10/10/14 | 2
[6 empty] | 140808-0641 Total |  |  | 12 | 12.93 | -0.93
15673 | OCCIDENTAL MALL | S | 140707-0239 | CLOSED | 10/20/14 | CHEMAQUA | Subcontract | 10/20/14 | 0.45
[6 empty] | 140707-0239 Total |  |  | 0.45 | 0.45 | 0
15769 | 601 PINE ST | S | 140707-1025 | CLOSED | 10/10/14 | COMMERCIAC | Subcontract | 10/10/14 | 0
[6 empty] | 140707-1025 Total |  |  | 0 | 1 | -1
16670 | KELLER ROHRBACK | C | 140613-0307 | CLOSED | 10/17/14 | HODGINSJ | Seattle Area | 10/17/14 | 2
[6 empty] | 140613-0307 Total |  |  | 2 | 1.5 | 0.5
17268 | PLANNED PARENTHOOD | S | 140707-0056 | CLOSED | 10/07/14 | WHITEM | HVAC SEATTLE | 10/07/14 | 3
[6 empty] | 140707-0056 Total |  |  | 3 | 3 | 0
|  | S | 140707-0510 | CLOSED | 10/07/14 | BATEE | HVAC SEATTLE | 10/07/14 | 3.75
[6 empty] | 140707-0510 Total |  |  | 3.75 | 3.75 | 0
|  | S | 140707-0820 | CLOSED | 10/07/14 | LARIVIERES | HVAC SEATTLE | 10/07/14 | 3.5
[6 empty] | 140707-0820 Total |  |  | 3.5 | 3.5 | 0
17269 | HOMEWOOD SUITES HOTEL | S | 140808-0300 | CLOSED | 10/21/14 | WHITEM | HVAC SEATTLE | 10/10/14 | 1.5
[6 empty] | WHITEM | HVAC SEATTLE | 10/21/14 | 2.5
[6 empty] | 140808-0300 Total |  |  | 4 | 4 | 0
17370 | NINTH & STEWART, LLC | S | 140707-0721 | CLOSED | 10/07/14 | OLSONB | HVAC SEATTLE | 10/06/14 | 1.25
[6 empty] | OLSONB | HVAC SEATTLE | 10/07/14 | 7
[6 empty] | LEEM | HVAC SEATTLE | 10/07/14 | 2
[6 empty] | 140707-0721 Total |  |  | 10.25 | 10.25 | 0
17475 | CENTRAL BUILDING | S | 140808-0304 | CLOSED | 10/08/14 | SONCRANTS | CHR SEATTLE | 10/08/14 | 8
[6 empty] | 140808-0304 Total |  |  | 8 | 5.98 | 2.02
|  | S | 140808-0547 | CLOSED | 10/22/14 | WHITEA | HVAC SEATTLE | 10/06/14 | 8
[6 empty] | DIXONM | HVAC SEATTLE | 10/13/14 | 3.5
[6 empty] | WHITEA | HVAC SEATTLE | 10/07/14 | 8
[6 empty] | WHITEA | HVAC SEATTLE | 10/09/14 | 8
[6 empty] | DIXONM | HVAC SEATTLE | 10/13/14 | 8
[6 empty] | WHITEA | HVAC SEATTLE | 10/13/14 | 4
[6 empty] | WHITEA | HVAC SEATTLE | 10/22/14 | 1.5
[6 empty] | WHITEA | HVAC SEATTLE | 10/22/14 | 2.5
[6 empty] | 140808-0547 Total |  |  | 43.5 | 55.11 | -11.61
17478 | 823 MARION-MARION COURT | S | 140707-0455 | CLOSED | 10/20/14 | CHEMAQUA | Subcontract | 10/20/14 | 0.01
[6 empty] | 140707-0455 Total |  |  | 0.01 | 0.01 | 0
17561 | HOLY NAMES ACADEMY | S | 140707-0240 | CLOSED | 10/10/14 | RUFFNERK | HVAC SEATTLE | 10/10/14 | 5
[6 empty] | 140707-0240 Total |  |  | 5 | 7.75 | -2.75
17585 | OUR LADY OF FATIMA CHURCH | S | 140808-1308 | CLOSED | 10/17/14 | LARIVIERES | HVAC SEATTLE | 10/17/14 | 4
[6 empty] | LARIVIERES | HVAC SEATTLE | 10/17/14 | 4.01
[6 empty] | 140808-1308 Total |  |  | 8.01 | 8.5 | -0.49
17750 | CONCORD CONDOMINIUMS | S | 140509-0837 | CLOSED | 10/14/14 | REGHETAO | HVAC SEATTLE | 10/14/14 | 6
[6 empty] | REGHETAO | HVAC SEATTLE | 10/14/14 | 2
[6 empty] | 140509-0837 Total |  |  | 8 | 8.54 | -0.54
|  | S | 140707-0241 | CLOSED | 10/10/14 | COMMERCIAC | Subcontract | 10/10/14 | 0
[6 empty] | 140707-0241 Total |  |  | 0 | 1 | -1
17753 | LAKE UNION LANDING | S | 140808-0301 | CLOSED | 10/08/14 | LEEM | HVAC SEATTLE | 10/08/14 | 3
[6 empty] | 140808-0301 Total |  |  | 3 | 3 | 0
17778 | LATENT PROCESS LAB | S | 140808-0085 | CLOSED | 10/08/14 | LARIVIERES | HVAC SEATTLE | 10/08/14 | 1.25
[6 empty] | 140808-0085 Total |  |  | 1.25 | 1.25 | 0
17789 | MILLENNIUM TOWER RESIDENTIAL | S | 140613-0389 | CLOSED | 10/20/14 | CHEMAQUA | Subcontract | 10/20/14 | 0.25
[6 empty] | 140613-0389 Total |  |  | 0.25 | 0.25 | 0
|  | S | 140707-0167 | CLOSED | 10/20/14 | CHEMAQUA | Subcontract | 10/20/14 | 0.25
[6 empty] | 140707-0167 Total |  |  | 0.25 | 0.25 | 0
17981 | GOLDMAN SACHS SEATTLE | S | 140707-0778 | CLOSED | 10/18/14 | WESTD | HVAC SEATTLE | 10/18/14 | 4
[6 empty] | OLSONB | HVAC SEATTLE | 10/18/14 | 4
[6 empty] | 140707-0778 Total |  |  | 8 | 7 | 1
18107 | THE WESTLAKE | S | 140808-0999 | CLOSED | 10/10/14 | WILDERG | HVAC SEATTLE | 09/30/14 | 3.5
[6 empty] | WILDERG | HVAC SEATTLE | 10/10/14 | 0.5
[6 empty] | 140808-0999 Total |  |  | 4 | 4.25 | -0.25
18240 | VERIZON WHITE CENTER | C | 140808-1334 | CLOSED | 10/20/14 | BIRDSELLS | HVAC S KING | 10/20/14 | 2
[6 empty] | 140808-1334 Total |  |  | 2 | 1.22 | 0.78
18566 | 3701 NORFOLK BUILDING | S | 140808-1393 | CLOSED | 10/16/14 | NAVOSA | HVAC SEATTLE | 10/16/14 | 7.25
[6 empty] | 140808-1393 Total |  |  | 7.25 | 7.2 | 0.05
18584 | MACDONALD-MILLER NORFOLK | D | 140808-0171 | CLOSED | 10/17/14 | ROSSOWJ | CHR SEATTLE | 10/13/14 | 8
[6 empty] | LARIVIERES | CHR SEATTLE | 10/07/14 | 2
[6 empty] | ROSSOWJ | CHR SEATTLE | 10/17/14 | 8
[6 empty] | 140808-0171 Total |  |  | 18 | 0.94 | 17.06
18700 | GGLO ARCHITECTS | C | 140808-1544 | CLOSED | 10/24/14 | INGLEK | HVAC SEATTLE | 10/24/14 | 1.75
[6 empty] | 140808-1544 Total |  |  | 1.75 | 1.75 | 0
18745 | METROPOLITAN PARK NORTH | S | 140808-0972 | CLOSED | 11/03/14 | WILDERG | HVAC SEATTLE | 10/10/14 | 3.75
[6 empty] | WILDERG | HVAC SEATTLE | 10/10/14 | 2.75
[6 empty] | WILDERG | HVAC SEATTLE | 10/10/14 | 5
[6 empty] | WILDERG | HVAC SEATTLE | 10/13/14 | 8
[6 empty] | 140808-0972 Total |  |  | 19.5 | 9.32 | 10.18
19272 | ALKI CONDO | D | 141002-0067 | CLOSED | 10/08/14 | NEWMANB | PLB SEATTLE | 10/06/14 | 1
[6 empty] | NEWMANB | PLB SEATTLE | 10/08/14 | 2
[6 empty] | 141002-0067 Total |  |  | 3 | 2.75 | 0.25
19387 | 1310 E UNION CONDOS | S | 140808-1240 | CLOSED | 10/08/14 | INGLEK | HVAC SEATTLE | 10/08/14 | 2.25
[6 empty] | 140808-1240 Total |  |  | 2.25 | 2.25 | 0
19563 | JEFFERSON TOWER | S | 140808-1138 | CLOSED | 10/14/14 | HOWDENR | CHR SEATTLE | 10/14/14 | 4.5
[6 empty] | 140808-1138 Total |  |  | 4.5 | 4.2 | 0.3
19637 | MENTE LLC | S | 140808-0733 | CLOSED | 10/10/14 | GIDEONS | BLR SEATTLE | 10/08/14 | 10.5
[6 empty] | GIDEONS | BLR SEATTLE | 10/10/14 | 1
[6 empty] | 140808-0733 Total |  |  | 11.5 | 10.5 | 1
|  | S | 140808-1083 | CLOSED | 10/08/14 | NAVOSA | HVAC SEATTLE | 10/08/14 | 4.5
[6 empty] | 140808-1083 Total |  |  | 4.5 | 4.5 | 0
19690 | ENVIRONMENTAL PROTECTION | C | 140707-1071 | CLOSED | 10/14/14 | OLSONB | HVAC SEATTLE | 10/14/14 | 6
[6 empty] | BATEE | HVAC SEATTLE | 10/14/14 | 2
[6 empty] | 140707-1071 Total |  |  | 8 | 9.75 | -1.75
21239 | JEAN GARDNER | S | 140929-0009 | CLOSED | 10/10/14 | LARIVIERES | HVAC SEATTLE | 10/10/14 | 3
[6 empty] | 140929-0009 Total |  |  | 3 | 2 | 1
22107 | MARKET COURT CONDO'S | C | 140808-0124 | CLOSED | 10/09/14 | WHITEM | HVAC SEATTLE | 10/09/14 | 1
[6 empty] | 140808-0124 Total |  |  | 1 | 1 | 0
|  | C | 140808-0765 | CLOSED | 10/09/14 | WHITEA | HVAC SEATTLE | 10/09/14 | 3
[6 empty] | 140808-0765 Total |  |  | 3 | 3 | 0
22783 | LEISURE CARE | S | 140707-0983 | CLOSED | 10/24/14 | LEEM | HVAC SEATTLE | 10/24/14 | 1.5
[6 empty] | 140707-0983 Total |  |  | 1.5 | 1.5 | 0
22836 | EDUCATIONAL RESOURCE AND ADMIN | S | 140715-0057 | CLOSED | 10/15/14 | SONCRANTS | CHR SEATTLE | 10/15/14 | 4
[6 empty] | 140715-0057 Total |  |  | 4 | 1.75 | 2.25
22960 | PACIFIC MARKET CENTER | S | 140707-0166 | CLOSED | 10/20/14 | WHITEA | HVAC SEATTLE | 09/10/14 | 7.5
[6 empty] | HODGINSJ | HVAC SEATTLE | 09/09/14 | 8
[6 empty] | WHITEA | HVAC SEATTLE | 09/11/14 | 8
[6 empty] | KRUEGERJ | HVAC SEATTLE | 09/15/14 | 2
[6 empty] | WHITEA | HVAC SEATTLE | 09/14/14 | 8
[6 empty] | WHITEA | HVAC SEATTLE | 09/14/14 | 7
[6 empty] | WHITEA | HVAC SEATTLE | 09/22/14 | 6.5
[6 empty] | WHITEA | HVAC SEATTLE | 10/01/14 | 2.25
[6 empty] | 140707-0166 Total |  |  | 49.25 | 57 | -7.75
23066 | HELSELL FETTERMAN LLC | S | 140808-0014 | CLOSED | 10/10/14 | WHITEA | HVAC SEATTLE | 10/10/14 | 1
[6 empty] | 140808-0014 Total |  |  | 1 | 1 | 0
23715 | MARCHEX | S | 140808-0915 | CLOSED | 10/14/14 | INGLEK | HVAC SEATTLE | 10/14/14 | 3.25
[6 empty] | 140808-0915 Total |  |  | 3.25 | 3.25 | 0
23802 | GGLO ARCHITECTS | S | 140808-1143 | CLOSED | 10/15/14 | NAVOSA | HVAC SEATTLE | 10/16/14 | 6
[6 empty] | 140808-1143 Total |  |  | 6 | 6 | 0
24258 | NORTHWEST KIDNEY CENTER | S | 140613-0761 | CLOSED | 10/16/14 | SONCRANTS | CHR SEATTLE | 10/16/14 | 2
[6 empty] | 140613-0761 Total |  |  | 2 | 2.5 | -0.5
24454 | CAROLINE KLINE GALLAND HOME | S | 140808-1432 | CLOSED | 10/20/14 | WHITEM | HVAC SEATTLE | 10/20/14 | 2
[6 empty] | 140808-1432 Total |  |  | 2 | 2 | 0
24676 | ALL STAR DIRECTORIES | S | 140707-0941 | CLOSED | 10/08/14 | OLSONB | HVAC SEATTLE | 10/08/14 | 1.5
[6 empty] | 140707-0941 Total |  |  | 1.5 | 1.5 | 0
24733 | SHORT CRESSMAN AND BURGESS | S | 140808-0149 | CLOSED | 10/21/14 | INGLEK | HVAC SEATTLE | 10/21/14 | 1.5
[6 empty] | 140808-0149 Total |  |  | 1.5 | 1.5 | 0
24933 | HOTEL 1000 SEWER-AM | S | 140707-0835 | CLOSED | 10/17/14 | NEWMANB | PLB SEATTLE | 10/17/14 | 8
[6 empty] | WOLFEB | PLB SEATTLE | 10/17/14 | 8
[6 empty] | 140707-0835 Total |  |  | 16 | 16.5 | -0.5
24934 | HOTEL 1000 GREASE DRAIN-PM | S | 140707-0610 | CLOSED | 10/17/14 | NEWMANB | PLB SEATTLE | 10/17/14 | 5
[6 empty] | WOLFEB | PLB SEATTLE | 10/17/14 | 5
[6 empty] | 140707-0610 Total |  |  | 10 | 10 | 0
25044 | FAIRVIEW RESEARCH CENTER | S | 140707-0877 | CLOSED | 10/23/14 | SCHRAMML | CHR SEATTLE | 10/23/14 | 5
[6 empty] | 140707-0877 Total |  |  | 5 | 8 | -3
25044BLR | FAIRVIEW RESEARCH CENTER | S | 140808-0657 | CLOSED | 10/20/14 | WHITEM | HVAC SEATTLE | 10/20/14 | 3
[6 empty] | 140808-0657 Total |  |  | 3 | 2.25 | 0.75
25054 | 5TH AND MADISON CONDOS | S | 140808-0494 | CLOSED | 10/16/14 | BATEE | HVAC SEATTLE | 10/16/14 | 2.5
[6 empty] | 140808-0494 Total |  |  | 2.5 | 1.5 | 1
25223 | BELLTOWN LOFTS CONDOS | S | 140707-1030 | CLOSED | 10/21/14 | WHITEM | HVAC SEATTLE | 10/21/14 | 2
[6 empty] | 140707-1030 Total |  |  | 2 | 2 | 0
25233 | CLOVERDALE BUSINESS PRK | S | 140707-0417 | CLOSED | 10/06/14 | LEEM | HVAC SEATTLE | 10/06/14 | 3
[6 empty] | 140707-0417 Total |  |  | 3 | 3.25 | -0.25
25268 | VERIZON RIVERVIEW | C | 140808-1473 | CLOSED | 10/20/14 | BIRDSELLS | HVAC S KING | 10/20/14 | 2
[6 empty] | 140808-1473 Total |  |  | 2 | 1.22 | 0.78
25418 | SOUTH 93RD BUSINESS PARK | S | 140707-0104 | CLOSED | 10/06/14 | LEEM | HVAC SEATTLE | 10/06/14 | 1.5
[6 empty] | 140707-0104 Total |  |  | 1.5 | 1.5 | 0
25432 | ING PIKE TOWER | S | 140808-0144 | CLOSED | 10/14/14 | INGLEK | HVAC SEATTLE | 10/14/14 | 1.5
[6 empty] | 140808-0144 Total |  |  | 1.5 | 1.5 | 0
25450 | 1521 2ND AVE CONDO COMMON | S | 140707-1029 | CLOSED | 10/10/14 | COMMERCIAC | Subcontract | 10/10/14 | 0
[6 empty] | 140707-1029 Total |  |  | 0 | 0.45 | -0.45
|  | S | 140808-0182 | CLOSED | 10/21/14 | LEEM | HVAC SEATTLE | 10/13/14 | 4
[6 empty] | HODGINSJ | HVAC SEATTLE | 10/17/14 | 6
[6 empty] | LEEM | HVAC SEATTLE | 10/15/14 | 8
[6 empty] | LEEM | HVAC SEATTLE | 10/16/14 | 4.5
[6 empty] | LEEM | HVAC SEATTLE | 10/24/14 | 5
[6 empty] | 140808-0182 Total |  |  | 27.5 | 33.66 | -6.16
|  | S | 140808-0881 | CLOSED | 10/08/14 | LARIVIERES | HVAC SEATTLE | 10/08/14 | 1.75
[6 empty] | 140808-0881 Total |  |  | 1.75 | 1.75 | 0
25481 | SOUTH 96TH BUSINESS PARK | S | 140707-0867 | CLOSED | 10/06/14 | LEEM | HVAC SEATTLE | 10/06/14 | 0.75
[6 empty] | 140707-0867 Total |  |  | 0.75 | 0.25 | 0.5
25526 | LAIRDNORTON WEALTH MANAGEMENT | S | 140808-0642 | CLOSED | 10/24/14 | LEEM | HVAC SEATTLE | 10/24/14 | 1.5
[6 empty] | 140808-0642 Total |  |  | 1.5 | 1.5 | 0
25649 | KENYON INDUSTRIAL PARK | S | 140707-0291 | CLOSED | 10/07/14 | LEEM | HVAC SEATTLE | 10/07/14 | 0.75
[6 empty] | LEEM | HVAC SEATTLE | 10/07/14 | 1.75
[6 empty] | 140707-0291 Total |  |  | 2.5 | 2.25 | 0.25
25921 | MADISON TWR RES BOILER/PUMPS | S | 140808-0500 | CLOSED | 10/15/14 | WHITEM | HVAC SEATTLE | 10/15/14 | 4
[6 empty] | 140808-0500 Total |  |  | 4 | 4.24 | -0.24
26048 | ADELAIDE CONDOS | S | 140808-0248 | CLOSED | 10/09/14 | INGLEK | HVAC SEATTLE | 10/09/14 | 5.75
[6 empty] | 140808-0248 Total |  |  | 5.75 | 5.75 | 0
30278 | HOTEL 1000 BOILER/PUMPS | S | 140707-0758 | CLOSED | 10/16/14 | WHITEM | HVAC SEATTLE | 10/02/14 | 2
[6 empty] | WHITEM | HVAC SEATTLE | 10/06/14 | 5
[6 empty] | WHITEM | HVAC SEATTLE | 10/16/14 | 1
[6 empty] | 140707-0758 Total |  |  | 8 | 8 | 0
30281 | MADISON TWR MST ASSO BOIL/PUMP | S | 140707-0710 | CLOSED | 10/16/14 | WHITEM | HVAC SEATTLE | 09/25/14 | 2
[6 empty] | WHITEM | HVAC SEATTLE | 10/02/14 | 2
[6 empty] | WHITEM | HVAC SEATTLE | 10/16/14 | 1
[6 empty] | 140707-0710 Total |  |  | 5 | 4.5 | 0.5
30646 | HOTEL 1000 SF AND EF | S | 140808-0034 | CLOSED | 10/17/14 | BATEE | HVAC SEATTLE | 10/15/14 | 6
[6 empty] | BATEE | HVAC SEATTLE | 10/17/14 | 4.5
[6 empty] | 140808-0034 Total |  |  | 10.5 | 10.25 | 0.25
30647 | HOTEL 1000 MSTR ASSO EFS | S | 140808-0122 | CLOSED | 10/15/14 | BATEE | HVAC SEATTLE | 10/15/14 | 2
[6 empty] | 140808-0122 Total |  |  | 2 | 2 | 0
30678 | EXPERIENCE MUSIC PROJECT | S | 140808-0520 | CLOSED | 10/13/14 | STEWARTA | CHR SEATTLE | 10/13/14 | 6
[6 empty] | 140808-0520 Total |  |  | 6 | 5.75 | 0.25
30988 | JACK HENRY AND ASSOCIATES | S | 140808-1560 | CLOSED | 10/24/14 | INGLEK | HVAC SEATTLE | 10/24/14 | 1
[6 empty] | 140808-1560 Total |  |  | 1 | 1 | 0
31399 | BMW OF SEATTLE | S | 140707-0881 | CLOSED | 10/16/14 | RUFFNERK | HVAC SEATTLE | 10/13/14 | 5
[6 empty] | RUFFNERK | HVAC SEATTLE | 10/14/14 | 4
[6 empty] | RUFFNERK | HVAC SEATTLE | 10/16/14 | 8
[6 empty] | 140707-0881 Total |  |  | 17 | 16.5 | 0.5
31418 | ARCTIC STORM MANAGMENT GROUP | S | 140707-0804 | CLOSED | 10/06/14 | LEEM | HVAC SEATTLE | 09/16/14 | 2
[6 empty] | LEEM | HVAC SEATTLE | 09/18/14 | 5
[6 empty] | LEEM | HVAC SEATTLE | 09/26/14 | 2
[6 empty] | 140707-0804 Total |  |  | 9 | 9.75 | -0.75
31476 | MARKET PLACE TOWER CT | S | 140707-0357 | CLOSED | 10/17/14 | REGHETAO | HVAC SEATTLE | 10/02/14 | 8
[6 empty] | REGHETAO | HVAC SEATTLE | 10/17/14 | 1
[6 empty] | 140707-0357 Total |  |  | 9 | 7.25 | 1.75
31792 | SAFECO CENTER | S | 140707-0433 | CLOSED | 10/20/14 | RUFFNERK | HVAC SEATTLE | 10/20/14 | 6
[6 empty] | 140707-0433 Total |  |  | 6 | 6.12 | -0.12
31793 | SAFECO PLAZA | S | 140707-0915 | CLOSED | 10/23/14 | RUFFNERK | HVAC SEATTLE | 10/23/14 | 7
[6 empty] | RUFFNERK | HVAC SEATTLE | 10/23/14 | 7
[6 empty] | 140707-0915 Total |  |  | 14 | 14.96 | -0.96
31906 | KING COUNTY ADMIN BUILDING | S | 140707-0162 | CLOSED | 10/06/14 | HOWDENR | CHR SEATTLE | 10/06/14 | 4
[6 empty] | 140707-0162 Total |  |  | 4 | 4 | 0
31908 | KING CO CORRECTIONAL FACILITY | S | 140707-0254 | CLOSED | 10/17/14 | ROSSOWJ | CHR SEATTLE | 10/17/14 | 8
[6 empty] | 140707-0254 Total |  |  | 8 | 32 | -24
31912 | WEST POINT TREATMENT PLANT | S | 140808-1167 | CLOSED | 10/15/14 | SONCRANTS | CHR SEATTLE | 10/15/14 | 4
[6 empty] | 140808-1167 Total |  |  | 4 | 3 | 1
31925 | WHITE PAGES | S | 140808-1203 | CLOSED | 10/20/14 | INGLEK | HVAC SEATTLE | 10/20/14 | 1.5
[6 empty] | 140808-1203 Total |  |  | 1.5 | 1.5 | 0
31939 | STADIUM INNOVATION CENTER | S | 140707-0181 | CLOSED | 10/06/14 | KRUEGERJ | HVAC SEATTLE | 09/18/14 | 2
[6 empty] | KRUEGERJ | HVAC SEATTLE | 09/15/14 | 2
[6 empty] | KRUEGERJ | HVAC SEATTLE | 09/25/14 | 2
[6 empty] | KRUEGERJ | HVAC SEATTLE | 10/06/14 | 2
[6 empty] | 140707-0181 Total |  |  | 8 | 8.22 | -0.22
|  | S | 140707-0954 | CLOSED | 10/10/14 | COMMERCIAC | Subcontract | 10/10/14 | 0
[6 empty] | 140707-0954 Total |  |  | 0 | 0.45 | -0.45
33328 | MADISON TOWER RESIDENTS | S | 140808-0238 | CLOSED | 10/21/14 | INGLEK | HVAC SEATTLE | 10/21/14 | 5.25
[6 empty] | 140808-0238 Total |  |  | 5.25 | 5.22 | 0.03
33346 | BROADCAST SERVICES INC | S | 140808-1157 | CLOSED | 10/22/14 | INGLEK | HVAC SEATTLE | 10/22/14 | 6
[6 empty] | 140808-1157 Total |  |  | 6 | 4 | 2
33393 | SEED IP LAW GROUP | S | 140808-0133 | CLOSED | 10/22/14 | INGLEK | HVAC SEATTLE | 10/22/14 | 2
[6 empty] | 140808-0133 Total |  |  | 2 | 2 | 0
33404 | AMERICAN SEAFOOD | S | 140707-0526 | CLOSED | 10/08/14 | OLSONB | HVAC SEATTLE | 10/08/14 | 1.5
[6 empty] | 140707-0526 Total |  |  | 1.5 | 1.5 | 0
33619 | 505 BUILDING MAIN | S | 140707-0442 | CLOSED | 10/23/14 | WILDERG | HVAC SEATTLE | 10/21/14 | 2
[6 empty] | WILDERG | HVAC SEATTLE | 10/23/14 | 8
[6 empty] | 140707-0442 Total |  |  | 10 | 10.58 | -0.58
|  | S | 140707-0586 | CLOSED | 10/21/14 | OLSONB | HVAC SEATTLE | 10/21/14 | 8.5
[6 empty] | 140707-0586 Total |  |  | 8.5 | 8.52 | -0.02
|  | S | 140808-0319 | CLOSED | 10/21/14 | CHEMTREAT | Subcontract | 10/21/14 | 0.04
[6 empty] | 140808-0319 Total |  |  | 0.04 | 0.04 | 0
33632 | ISILON CT 3 ONLY | S | 140707-0232 | CLOSED | 10/17/14 | CHUTICHJ | Seattle Area | 10/17/14 | 0.15
[6 empty] | 140707-0232 Total |  |  | 0.15 | 0.15 | 0
|  | S | 140707-0814 | CLOSED | 10/20/14 | CHEMTREAT | Subcontract | 10/20/14 | 0
[6 empty] | 140707-0814 Total |  |  | 0 | 0 | 0
33677 | QUALCOMM, INC. | S | 140808-0906 | CLOSED | 10/08/14 | LEEM | HVAC SEATTLE | 10/08/14 | 3
[6 empty] | 140808-0906 Total |  |  | 3 | 3 | 0
33744 | PHYSICIANS INSURANCE | S | 140808-1397 | CLOSED | 10/13/14 | REGHETAO | HVAC SEATTLE | 10/13/14 | 2
[6 empty] | 140808-1397 Total |  |  | 2 | 1.5 | 0.5
33763 | HOME PLATE CENTER BLDG 1 | S | 140707-0356 | CLOSED | 10/10/14 | COMMERCIAC | Subcontract | 10/10/14 | 0
[6 empty] | 140707-0356 Total |  |  | 0 | 0.01 | -0.01
33851 | BLANCHARD PLAZA | S | 140707-1031 | CLOSED | 10/22/14 | WHITEM | HVAC SEATTLE | 10/22/14 | 6.5
[6 empty] | 140707-1031 Total |  |  | 6.5 | 6.5 | 0
33859 | SIXTH & LENORA APARTMENTS | S | 140613-0869 | CLOSED | 10/20/14 | WHITEM | HVAC SEATTLE | 07/22/14 | 3
[6 empty] | WHITEM | HVAC SEATTLE | 07/28/14 | 3
[6 empty] | WHITEM | HVAC SEATTLE | 08/05/14 | 2.5
[6 empty] | WHITEM | HVAC SEATTLE | 08/04/14 | 5.5
[6 empty] | WHITEM | HVAC SEATTLE | 08/04/14 | 8
[6 empty] | HOWDENR | HVAC SEATTLE | 08/07/14 | 8
[6 empty] | WHITEM | HVAC SEATTLE | 08/11/14 | 5
[6 empty] | WHITEM | HVAC SEATTLE | 08/25/14 | 4
[6 empty] | WHITEM | HVAC SEATTLE | 08/18/14 | 4
[6 empty] | WHITEM | HVAC SEATTLE | 08/18/14 | 2
[6 empty] | WHITEM | HVAC SEATTLE | 08/26/14 | 6
[6 empty] | WHITEM | HVAC SEATTLE | 10/01/14 | 2
[6 empty] | WHITEM | HVAC SEATTLE | 10/20/14 | 1
[6 empty] | WHITEM | HVAC SEATTLE | 10/20/14 | 2
[6 empty] | 140613-0869 Total |  |  | 56 | 41.75 | 14.25
33898 | DELOITTE DT | S | 140707-0728 | CLOSED | 10/16/14 | LARIVIERES | HVAC SEATTLE | 10/16/14 | 6.5
[6 empty] | 140707-0728 Total |  |  | 6.5 | 6.5 | 0
34008 | EQUINIX SE3 FACILITY | S | 140707-0337 | CLOSED | 10/05/14 | LARIVIERES | HVAC SEATTLE | 09/23/14 | 6
[6 empty] | LARIVIERES | HVAC SEATTLE | 09/26/14 | 6
[6 empty] | LARIVIERES | HVAC SEATTLE | 09/26/14 | 3
[6 empty] | LARIVIERES | HVAC SEATTLE | 10/02/14 | 5
[6 empty] | LARIVIERES | HVAC SEATTLE | 10/03/14 | 9
[6 empty] | LARIVIERES | HVAC SEATTLE | 10/05/14 | 10
[6 empty] | 140707-0337 Total |  |  | 39 | 30.67 | 8.33
|  | S | 140707-0753 | CLOSED | 10/10/14 | COMMERCIAC | Subcontract | 10/10/14 | 0
[6 empty] | 140707-0753 Total |  |  | 0 | 0.25 | -0.25
34022 | CTS SEATTLE NODE SITE | S | 140707-0441 | CLOSED | 10/06/14 | OLSONB | HVAC SEATTLE | 10/06/14 | 4.25
[6 empty] | 140707-0441 Total |  |  | 4.25 | 4.25 | 0
34032ERC | YMCA EAST MADISON | S | 140411-0650 | CLOSED | 10/08/14 | NOELG | Commissioning | 09/02/14 | 0
[6 empty] | NOELG | Commissioning | 09/24/14 | 3
[6 empty] | NOELG | Commissioning | 09/24/14 | 0.5
[6 empty] | 140411-0650 Total |  |  | 3.5 | 4 | -0.5
|  | S | 140613-0603 | CLOSED | 10/08/14 | NOELG | Commissioning | 09/03/14 | 1
[6 empty] | NOELG | Commissioning | 09/03/14 | 4.5
[6 empty] | OSBORNEA | Commissioning | 09/22/14 | 5
[6 empty] | OSBORNEA | Commissioning | 08/19/14 | 1
[6 empty] | OSBORNEA | Commissioning | 08/20/14 | 1
[6 empty] | NOELG | Commissioning | 09/24/14 | 3
[6 empty] | NOELG | Commissioning | 09/24/14 | 3
[6 empty] | NOELG | Commissioning | 09/24/14 | 1.5
[6 empty] | NOELG | Commissioning | 09/24/14 | 2
[6 empty] | OSBORNEA | Commissioning | 10/08/14 | 1
[6 empty] | 140613-0603 Total |  |  | 23 | 4 | 19
34033ERC | YMCA DOWNTOWN | S | 140707-0667 | CLOSED | 10/14/14 | NOELG | Commissioning | 09/25/14 | 1
[6 empty] | RICHMONDJ | Commissioning | 09/15/14 | 2
[6 empty] | RICHMONDJ | Commissioning | 09/17/14 | 4
[6 empty] | 140707-0667 Total |  |  | 7 | 4 | 3
34065 | CAPITOL ONE COFFEE BARS | S | 140613-0188 | CLOSED | 10/09/14 | OLSONB | HVAC SEATTLE | 10/09/14 | 6
[6 empty] | 140613-0188 Total |  |  | 6 | 8.75 | -2.75
34093 | 1001 BROADWAY BUILDING | S | 140707-0634 | CLOSED | 10/09/14 | ZELLERT | HVAC SEATTLE | 10/01/14 | 4
[6 empty] | ZELLERT | HVAC SEATTLE | 10/02/14 | 6
[6 empty] | ZELLERT | HVAC SEATTLE | 10/03/14 | 4.5
[6 empty] | ZELLERT | HVAC SEATTLE | 10/09/14 | 4.5
[6 empty] | 140707-0634 Total |  |  | 19 | 21.56 | -2.56
34094 | 101 NICKERSON BUILDING | S | 140707-0855 | CLOSED | 10/08/14 | OLSONB | HVAC SEATTLE | 10/08/14 | 2.5
[6 empty] | 140707-0855 Total |  |  | 2.5 | 2.5 | 0
34180 | VERIZON EASTLAKE | C | 140808-0785 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-0785 Total |  |  | 0 | 2 | -2
34182 | VERIZON GENESEE HILL | C | 140808-1059 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-1059 Total |  |  | 0 | 2 | -2
34195 | VERIZON U. DISTRICT | C | 140808-0952 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-0952 Total |  |  | 0 | 2 | -2
34197 | VERIZON 4TH & SENECA | C | 140808-1557 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-1557 Total |  |  | 0 | 2 | -2
34199 | VERIZON 5TH & PIKE | C | 140808-0258 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0258 Total |  |  | 0 | 2 | -2
34202 | VERIZON ALKI POINT | C | 140808-0068 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0068 Total |  |  | 0 | 2 | -2
34204 | VERIZON ARBORETUM | C | 140808-0479 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0479 Total |  |  | 0 | 2 | -2
34207 | VERIZON AURORA BRIDGE | C | 140808-1353 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-1353 Total |  |  | 0 | 2 | -2
34221 | VERIZON BRIERCREST | C | 140808-0041 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 2
[6 empty] | 140808-0041 Total |  |  | 2 | 2 | 0
34238 | VERIZON DISCOVERY PARK | C | 140808-0909 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-0909 Total |  |  | 0 | 2 | -2
34242 | VERIZON EAST FREEMONT | C | 140808-0240 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0240 Total |  |  | 0 | 2 | -2
34243 | VERIZON EAST JEFFERSON | C | 140808-0236 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0236 Total |  |  | 0 | 2 | -2
34244 | VERIZON EAST MADISON | C | 140808-0551 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 2
[6 empty] | 140808-0551 Total |  |  | 2 | 2 | 0
34264 | VERIZON GUMBALL | C | 140808-0114 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0114 Total |  |  | 0 | 2 | -2
34269 | VERIZON HIGHLANDS | C | 140808-1081 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-1081 Total |  |  | 0 | 2 | -2
34271 | VERIZON HOLMAN RD | C | 140808-0049 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0049 Total |  |  | 0 | 2 | -2
34280 | VERIZON KIDS | C | 140808-0778 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 2
[6 empty] | 140808-0778 Total |  |  | 2 | 2 | 0
34293 | VERIZON LAURELHURST | C | 140808-1540 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-1540 Total |  |  | 0 | 2 | -2
34295 | VERIZON LESCHI | C | 140808-0109 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0109 Total |  |  | 0 | 2 | -2
34301 | VERIZON MARTIN LUTHER KING BLV | C | 140808-1317 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-1317 Total |  |  | 0 | 2 | -2
34322 | VERIZON NIKO | C | 140808-1349 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-1349 Total |  |  | 0 | 2 | -2
34324 | VERIZON NORTH ACRES PARK | C | 140808-1207 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-1207 Total |  |  | 0 | 2 | -2
34337 | VERIZON PIONEER SQUARE | C | 140808-0412 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0412 Total |  |  | 0 | 2 | -2
34341 | VERIZON PORTAGE BAY | C | 140808-0340 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0340 Total |  |  | 0 | 2 | -2
|  | C | 141007-0049 | CLOSED | 10/22/14 | RENNERE | HVAC N SOUND | 10/22/14 | 2.75
[6 empty] | 141007-0049 Total |  |  | 2.75 | 2.76 | -0.01
34347 | VERIZON RICHMOND BEACH | C | 140808-0225 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0225 Total |  |  | 0 | 2 | -2
34353 | VERIZON SAW | C | 140808-0439 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0439 Total |  |  | 0 | 2 | -2
34355 | VERIZON SEWARD PARK | C | 140808-0346 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0346 Total |  |  | 0 | 2 | -2
|  | C | 141007-0055 | CLOSED | 10/22/14 | RENNERE | HVAC N SOUND | 10/22/14 | 2.75
[6 empty] | 141007-0055 Total |  |  | 2.75 | 2.76 | -0.01
34362 | VERIZON SOUTH JEFFERSON PARK | C | 140808-0693 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-0693 Total |  |  | 0 | 2 | -2
34363 | VERIZON SOUTH LAKE UNION | C | 140808-1354 | CLOSED | 10/09/14 | KLEMANNT |  | 10/09/14 | 0
[6 empty] | 140808-1354 Total |  |  | 0 | 2 | -2
34369 | VERIZON ST. REGIS | C | 140808-1350 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-1350 Total |  |  | 0 | 2 | -2
34383 | VERIZON WEDGEWOOD | C | 140808-0160 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0160 Total |  |  | 0 | 2 | -2
|  | C | 141007-0042 | CLOSED | 10/22/14 | RENNERE | HVAC N SOUND | 10/22/14 | 2
[6 empty] | 141007-0042 Total |  |  | 2 | 2.76 | -0.76
34384 | VERIZON WEST DENNY WAY | C | 140808-0164 | CLOSED | 10/08/14 | KLEMANNT |  | 10/08/14 | 0
[6 empty] | 140808-0164 Total |  |  | 0 | 2 | -2
34391 | VERIZON WOODLAND PARK | C | 140808-0719 | CLOSED | 10/07/14 | KLEMANNT |  | 10/07/14 | 0
[6 empty] | 140808-0719 Total |  |  | 0 | 2 | -2
34439 | FREMONT BUILDING | S | 140808-0938 | CLOSED | 10/24/14 | HODGINSJ | Seattle Area | 10/17/14 | 6
[6 empty] | HODGINSJ | Seattle Area | 10/20/14 | 6
[6 empty] | HODGINSJ | Seattle Area | 10/24/14 | 2
[6 empty] | 140808-0938 Total |  |  | 14 | 14 | 0
34463 | CENTURY SQUARE URS CORP | S | 140808-0913 | CLOSED | 10/24/14 | INGLEK | HVAC SEATTLE | 10/24/14 | 2
[6 empty] | 140808-0913 Total |  |  | 2 | 2 | 0
34637 | WATERMARK RESIDENTIAL 701 | S | 140905-0595 | CLOSED | 10/29/14 | REGHETAO | HVAC SEATTLE | 10/29/14 | 1.5
[6 empty] | 140905-0595 Total |  |  | 1.5 | 1.5 | 0
34639 | ALKI CSO FACILITY - ROF | S | 140707-0122 | CLOSED | 10/08/14 | RUFFNERK | HVAC SEATTLE | 10/08/14 | 2.25
[6 empty] | 140707-0122 Total |  |  | 2.25 | 2.5 | -0.25
34640 | ELLIOT WEST CSO FACILITY - ROF | S | 140707-0481 | CLOSED | 10/08/14 | RUFFNERK | HVAC SEATTLE | 10/08/14 | 2
[6 empty] | 140707-0481 Total |  |  | 2 | 2 | 0
34641 | CARKEEK CSO FACILITY - ROF | S | 140707-0708 | CLOSED | 10/08/14 | RUFFNERK | HVAC SEATTLE | 10/08/14 | 1.5
[6 empty] | 140707-0708 Total |  |  | 1.5 | 1.5 | 0
34644ERC | LAKE UNION BULDING ERC | S | 140613-0604 | CLOSED | 10/14/14 | CULPE | Commissioning | 10/14/14 | 4
[6 empty] | OSBORNEA | Commissioning | 08/05/14 | 8
[6 empty] | OSBORNEA | Commissioning | 08/06/14 | 2
[6 empty] | CULPE | Commissioning | 10/14/14 | 4
[6 empty] | 140613-0604 Total |  |  | 18 | 4 | 14
|  | S | 140808-0170 | CLOSED | 10/15/14 | CULPE | Commissioning | 10/15/14 | 8
[6 empty] | 140808-0170 Total |  |  | 8 | 4 | 4
34670 | REALNETWORKS INC | S | 140707-0989 | CLOSED | 10/10/14 | OLSONB | HVAC SEATTLE | 10/10/14 | 4
[6 empty] | 140707-0989 Total |  |  | 4 | 4 | 0
34671 | HOME PLATE CENTER BLDG 2 | S | 140707-0394 | CLOSED | 10/10/14 | COMMERCIAC | Subcontract | 10/10/14 | 0
[6 empty] | 140707-0394 Total |  |  | 0 | 0.45 | -0.45
34850 | CHANCERY CONDOS | S | 140701-0073 | CLOSED | 10/10/14 | WHITEM | HVAC SEATTLE | 10/10/14 | 1.5
[6 empty] | 140701-0073 Total |  |  | 1.5 | 1.5 | 0
35020 | RHAPSODY | S | 140821-0028 | CLOSED | 10/17/14 | NAVOSA | HVAC SEATTLE | 10/17/14 | 2
[6 empty] | 140821-0028 Total |  |  | 2 | 2 | 0
35026 | AT&T SAFECO FIELD DAS VENUE | S | 140923-0032 | CLOSED | 10/23/14 | SKINNERJ | HVAC S KING | 10/23/14 | 3.5
[6 empty] | 140923-0032 Total |  |  | 3.5 | 1.76 | 1.74
35064 | SCARGO APTS AND ADMIN | C | 140902-0076 | CLOSED | 10/09/14 | BLACKK | HVAC SEATTLE | 10/08/14 | 8.5
[6 empty] | REGHETAO | HVAC SEATTLE | 10/08/14 | 8.5
[6 empty] | NAVOSA | HVAC SEATTLE | 10/07/14 | 8
[6 empty] | REGHETAO | HVAC SEATTLE | 10/09/14 | 8
[6 empty] | BLACKK | HVAC SEATTLE | 10/09/14 | 2
[6 empty] | 140902-0076 Total |  |  | 35 | 15.75 | 19.25
35105 | WATERMARK TOWERSUTHERLAND#1505 | S | 141009-0037 | CLOSED | 10/09/14 | REGHETAO | HVAC SEATTLE | 10/09/14 | 1
[6 empty] | 141009-0037 Total |  |  | 1 | 1 | 0
|  | S | 141009-0097 | CLOSED | 10/15/14 | REGHETAO | HVAC SEATTLE | 10/15/14 | 1.25
[6 empty] | 141009-0097 Total |  |  | 1.25 | 1 | 0.25
60601 | MACDONALD-MILLER CONSTRUCTION | D | 140808-0572 | CLOSED | 10/06/14 | WHITEA | HVAC SEATTLE | 10/03/14 | 6
[6 empty] | BATEE | HVAC SEATTLE | 10/02/14 | 4
[6 empty] | WHITEA | HVAC SEATTLE | 10/06/14 | 1
[6 empty] | 140808-0572 Total |  |  | 11 | 12.75 | -1.75
| Seattle Area Total: | [7 empty] | 1136.21 | 1198.19 | -61.98